## Лист1
Application | TO DO | Possibility | Duration, hours | Price, $ | RATE
Family Book | Issue date to be optional on UI and Backend | YES | 3 | 90 | 30 | h\$
| Make Place of issue drop list with UAE Emirates | YES | 3 | 90
Dependent - Child | If resident status is No, Hide Emirates ID Start date and End date from UI and realign fields. | YES | 5 | 150
| For Expats - If resident status is YES, Visa Start and End Date, Passport Start and End Date should also be mandatory along with Emirates ID Start date and End date. | YES | 6 | 180
Dependent – Spouse | If resident status is No, Hide Emirates ID Start date and End date from UI. | YES | 4 | 120
| If resident status is YES, Visa Start and End Date, Passport Start and End Date should also be mandatory along with Emirates ID Start date and End date. | YES | 7 | 210
Dependents | Allow space to be entered for First, Second, Third and last name fields including Arabic names as well | YES | 8 | 240
Unified No | Increase no of characters to update Emirates ID – 15 | YES | 8 | 240
| Make Place of issue drop list with UAE Emirates | YES | 6 | 180
Personal Document – Passport | Increase no of characters to 9 | YES | 2 | 60
Address | Add Street and House No & Region field as display field in FIORI profile page next to Address type: Sequence of fields: Address Type, Street and House No, City, Country | YES | 5 | 150
Emergency Contact No | Change sub type label to ‘Emergency – Next of Kin Contact’; no of characters to increase to 40 as unable to enter full email if needed; should allow alpha numerical values | YES | 8 | 240
|  | TOTAL | 65 | 1950
STAGES
Discovery | 25.10.2021 - 28.10.2021
Development |  |  | 28.10.2021-18.11.2021
Testing |  |  |  | 8.11.2021-22.11.2021
Release |  |  |  |  | 22.11.2021-23.11.2021